Indigenous Community Uplift Metrics Initiative

Improving funding metrics to facilitate achievement of sustained indigenous community capability uplift

Concept outline

# Table of Contents

1	Summary	2

1.1.1	The problem	2

1.1.2	The solution	2

1.1.3	The project	2

2	Introduction	3

2.1	About this document	3

2.2	The document’s target outcome	3

2.3	An outline of the full set of initiatives	3

3	The Problem	4

3.1	The problem to be solved	4

3.2	The solution concept	4

3.3	Problem context	4

4	The Project	6

4.1	Introduction	6

4.2	Objective	6

4.2.1	Objective sub-components	6

4.3	Initiative Implementation Components	6

4.4	Notes and broad aims of the project	7

5	Appendices	8

5.1	Principles	8

5.2	Glossary	8

5.3	Existing problems	10

5.4	Potential initial metrics	13

5.5	Initiative component list	20

5.6	References	23

# Summary

### The problem

Current government funding for provision of services to indigenous communities is based on activity and output rather than benefits and outcomes.

That is, government agencies fund initiatives based on “number of widgets processed” (activity and outputs) rather than on how the “widgets” being funded contribute to community capability uplift (benefits and outcomes).

The result is a disconnect between government funding and stated aims of sustained community capability uplift.

### The solution

To address this, what’s needed is a framework of metrics that will guide the selection and measurement of government funding for services to indigenous communities that prompts providers to focus their efforts on creating high-quality and robust support for sustained community capability uplift.

What’s needed is a framework that uses explicit requirements and nudges to shift providers towards focusing on identifying and proving the real benefits their activities create, rather than stopping at the simple provision of services of indeterminate value.

To the best of our knowledge there is nothing of this type that exists at present.

We need to work together to create this framework.

### The project

The aim is to create a community-lead project to investigate, design and create a funding metrics framework explicitly tied to community capability uplift goals.

This will be a multi-year project involving the development of an innovative and robust framework through extensive consultation with key stakeholders, careful design by specialist experts, metrics that strongly encourage the required improvement, and academically rigorous testing.

Right now, this is just an idea.

We need to bring together the people who can help turn the idea into a project to create and implement a framework.

Further detail is available at www.malcher.co/p-f/community-metrics.

# Introduction

## About this document

This document outlines the broad concept of the “Community Uplift Metrics Initiative”.

## The document’s target outcome

The target outcome from this document is to build broad support for the concept of a Community Uplift Metrics Initiative, and to build up active participation in more comprehensively defining the initiative.

This document does not aim to fully define the initiative, to fully define the framework, nor to fully define the practicalities of implementation of the framework. Instead, the document builds the conceptual case for an initiative, and lays the groundwork for future steps, such as formal business case development and stakeholder engagement.

## An outline of the full set of initiatives

To achieve the full set of aims outlined here, multiple initiatives will be required.

This document outlines the first of these.

Key steps will be;

- Initiative concept outline

  - This document. Outlines the concept of the initiative.

- Business case

  - A future document will put forward the value and potential cost of the initiative.

- Project plan

  - A more detailed plan for implementation of the project to create the framework.

- First project – Framework creation

  - The first project is the initiative described by this document. It will create the framework – through research, extensive stakeholder engagement, and focused framework design and review activities.

- Second project – Technology creation

  - A subsequent initiative will create the technology to enable enacting the framework.

- Third project – Framework implementation

  - A third initiative will implement the framework.

# The Problem

## The problem to be solved

The core issue being addressed can be summarised as;

Disadvantage in indigenous communities is continuing across generations partly because the measures and metrics on which decisions are made and funding is allocated are not sufficiently connected to the long-term outcomes the communities need to properly control their own lives.

Disadvantage in indigenous communities is continuing across generations. Billions of dollars of government funding has been spent over decades with very little to show for it. Clearly there is something wrong with what is being done with that money.

A significant proportion of this problem exists because the measures and metrics used by government agencies to fund service provision in indigenous communities is not sufficiently connected to the long-term outcomes the communities need to be able to properly control their own lives.

Current government funding for provision of services to indigenous communities is based on activity and output rather than benefits and outcomes.

That is, government agencies fund initiatives based on “number of widgets processed” (activity and outputs) rather than on how the “widgets” being funded contribute to community capability uplift (benefits and outcomes).

The result is a disconnect between government funding and stated aims of sustained community capability uplift.

## The solution concept

We need a framework of metrics that will guide the selection and measurement of government funding for services to indigenous communities that requires providers to focus their efforts on creating high-quality and robust support for sustained community capability uplift.

We need a framework that uses explicit requirements and nudges to shift providers towards focusing on identifying and proving the real benefits their activities create, rather than stopping at the simple provision of services of indeterminate value.

To the best of our knowledge there is nothing of this type that exists at present.

We need to work together to create this framework.

## Problem context

Community development initiatives are often designed and deployed without the meaningful consultation of local community leaders. In addition to community consultation, funding initiatives are not sufficiently connected to measurable community development outcomes. At the present there is no standardised framework for measuring community development outcomes and evaluating the outcome of funding initiatives.

Policy research shows that outcomes from government community development schemes with indigenous communities often fail to provide socio-political benefits for the communities it seeks to help (Sharma Wallace et al, 2020; Doering et al 2021; Dodson & Smith, 2003; Markham et al, 2020).

Findings from research in Aotearoa New Zealand show that programs often fail to account for indigenous power, history, and context when designing and evaluating outcomes from funding initiatives (Sharma Wallace et al, 2020). Indigenous research in the Arctic has also been critical of the lack of cooperation and involvement of indigenous groups involved in government programs (Doering et al 2021). Similar findings are revealed in the Australian context where research shows a “governance gap” between governments and remote indigenous communities (Markham et al, 2020). Paramount to the research is the need for indigenous community inclusion in the development, design, and evaluation of funding schemes and interventions in the community.

A key outcome of the research illustrates the central role that “funding agencies” serve in enabling “meaningful collaboration” with indigenous groups (Markham et al, 2020: 1). In addition to the inclusion of local indigenous communities in the design and consultation of community development schemes, a framework is required to ensure that community funding is delivered in accordance with best-practice advice.

A number of organisations have created critical concepts and frameworks in important focal areas for social improvement, including Cape York Partnership’s Community Capability model (built from Amartya Sen’s Capability approach – Sen, 1999). Nevertheless, these capabilities have not yet been applied in a measurable way, are implemented in siloed approaches, and are often not continued over the extended time periods required to demonstrate true change.

A consistent national framework for remote community capability uplift will help streamline funding and implement a community first approach which centres around outcomes that empower the community, rather than the organisation(s) seeking funding. Most of all, a national framework will ensure funding activities are associated with long-term outcomes for the community.

# The Project

## Introduction

Introducing the aims and principles of the proposed Community Uplift Metrics Initiative.

## Objective

The initiative has one overriding purpose

To design a national framework to measure social development in remote Australian Indigenous communities. The framework will be outcome-focused, and centre on both community capability uplift and social empowerment.

To develop a framework that can guide the measurement and direction of future funding initiatives for remote Australian Indigenous communities. The framework will be flexible to the different socio-cultural needs of communities and focus on community capability uplift, rather than outputs of delivery.

### Objective sub-components

The aim includes;

- Finding a way to improve ability of communities to take control of their own lives. We’re addressing the metrics angle of this.

- Use the frameworks developed to encourage better interventions that have long-lasting positive impact on remote indigenous communities.

## Initiative Implementation Components

Conceptually, the components of this initiative include;

- Establish community and expert engagement and active commitment to define and drive the initiative.

- Engage experts, communities, government representatives and other key interested parties to identify the best metrics that will help influence future improvement of the health of all remote communities.

- Define the parts needed to build capability in remote communities

- Operating in alignment with the principle that “What gets measured gets done”, create metrics which will actively and positively influence the design of future projects and funding by defining the metrics by which the success (or otherwise) of such projects will be determined.

A detailed list of proposed initiative components is available in Section 5.5 – “Initiative component list”, 20, below.

## Notes and broad aims of the project

- The aim is to create a community-lead project to investigate, design and create a funding metrics framework explicitly tied to community capability uplift goals.

- This will be a multi-year project involving the development of an innovative and robust framework through extensive consultation with key stakeholders, careful design of appropriate principles by specialist experts, metrics that strongly encourage the required improvement, and academically rigorous testing.

- There are many ways this issue needs to be addressed. This particular initiative focuses on the metrics used for funding activities, and the impact such metrics have on provider’s behaviour when used to determine funding. It focuses on designing metrics to be applied to funding that will guide providers towards more positively impactful approaches.

- The aim of this initiative is to improve indigenous communities ability to independently manage and improve their own lives. That is, to uplift community capability, building on Amartya Sen’s concept of (community) capability.

- It is important that the framework creation initiative be driven by, and controlled by, non-government groups. Indigenous communities, community bodies, academics with expertise in the field.

- To this point, review of academic sources and conversations with indigenous leaders have firmly supported the hypothesis – that current funding metrics do not sufficiently link funding to community capability uplift.

  - We would welcome correction on this point – an existing framework that could be adopted would significantly reduce the effort, and time, to design and implementation.

- My personal aim in this work is to spark the idea, and advise the creation, and then hand over to a body of experts and driven stakeholders to make it happen.

- A slide deck providing further explanation is available here:

Right now, this is just an idea.

We need to turn the idea into a project to create and implement a framework.

# Appendices

## Principles

The following principles have been developed to guide the design of the initiative and the framework.

| Principle | Description | Comment |
| --- | --- | --- |
| Focused on measurement of outcome, rather than output | Community outcomes should be prioritised rather than organisational outputs (or inputs), |  |
| Inclusive of socio-political change | Factors such as choice and self-determination need to be considered in addition to other common social and economic conditions (such as health, housing). |  |
| Evidence-based | All metrics, data and methods should be based on robust evidence, solid reasoning, and clear logic. |  |
| Transparent | All frameworks, and methods should be open to review and scrutiny (with appropriate restrictions for individual privacy) |  |
| Flexible and inclusive | Not all communities have the same needs. The initiative will be designed with community leaders and experts. The framework needs to be adaptable to different community needs while supporting an overarching principle of community capability uplift |  |
| Built on iterative improvement | Continuous improvement etc should be embedded in all parts – from defining the problem and direction of the solution to the design of implementation components. Continuous improvement is built in to all aspects of the initiative |  |
| Built on input from expert and impacted contributors | Wide-spread collaboration and co-design with expert contributors and authoritative representation from impacted communities. Continuous and iterative improvement should happen through talking to people and building on people’s specialist expertise. |  |
| Use and build on what already exists | Where we find that a framework / model / system already exists that resolves any of the issues being addressed, we should utilise that model as far as practically possible. |  |

## Glossary

| Term | Acronym / abbreviation | Definition | Definition Source | Comments |
| --- | --- | --- | --- | --- |
| Cape York Partnership | CYP | The concept for this initiative started as a result of work being done by Cape York Partnership (CYP) in 2022. | CYP web site. |  |
| Community Capability | Capability | An ability of the community to do something. Generally refers to the ability of a community to take control of its future and lift itself up to a better state. | Created for this document. | Built on work by Amartya Sen, 1999. |
| Community capability uplift | Capability uplift | To improve a community’s ability to take control of its future. | Created for this document. |  |
| Community Uplift Metrics | Community Metrics | The shortened name of the overarching initiative. | Created for this document. |  |
| In-Community / Local |  | Services / equipment etc physically based in the indigenous community being targeted. | Created for this document. |  |
| Indigenous Community | Community | A group of Australian Aboriginal or Torres Strait Islander people, or those descended from Australian Aboriginal or Torres Strait Islander people. | Created for this document. |  |
| Metrics |  | A measure of some form. In the case of this document, the metrics refer to measurements of important aspects of community capability outcomes. | Created for this document. |  |
| Positive liberty |  |  | Isaiah Berlin, 1969 |  |
| Proxy measures |  | Proxy measures, as used here, are measures of inputs to capability uplift, rather than proof that capability has been raised. These measures are available now and, while they may not conclusively prove improvement in a community's capabilities, they do indicate that work is underway to create that improvement. Critically, proxy measures are also easier (and less costly) to collect and monitor. | Created for this document. |  |

## Existing problems

An indication of some existing problems in indigenous communities, community uplift metrics and data about community uplift metrics.

| Category | Problem | Benefits of addressing this problem | Solution Concept | Comments |
| --- | --- | --- | --- | --- |
| Timing | The solution is too difficult, and too big a project. |  | The solution to this is a long-term project. This could easily be 10 years to completion. |  |
| Subjectivity | Some of the most important findings appear to be subjective conclusions, without clear data substantiating them. |  |  |  |
| National approach | Lack of consistent national approach to data collection |  |  |  |
| Metric viability | Different metrics used by different communities, different researches, and government agencies. |  | A single consistent model for defining and measuring important areas of community development has the potential to enhance not just data scope and quality, but also shared understanding of what is important to focus on, and shared understanding of how to prove value. We need to get the experts in the room to sort out the differences across models - agree on gaps, overlaps and connection points across models. |  |
| Metric value | Metrics used may not focus on most important areas. |  |  |  |
| Metric linkages | It’s difficult to understand, and particularly to track, the relationship between measures on the ground and the broader long-term national outcomes individual initiatives are supposed to support. |  |  |  |
| Metric focus | Measurements often focus on metrics of "businesses", inputs or outputs, rather than outcomes that prove real and sustained change for the communities in question. |  |  |  |
| Metric focus | There is not universal agreement on what we should be aiming for. Community capability uplift is one perspective, but it’s not the only one. |  |  |  |
| Metric focus | We don’t know whether the metrics we’re using are the right ones to actively contribute to long-term social change and capability development |  |  |  |
| Lessons | Lessons in one area aren’t applied to another, and aren’t in shared data. |  |  |  |
| Language | Lack of consistent definitions for concepts and language used. |  |  |  |
| Historical information | Loss of historical information. Some great methods and metrics have been created in the past, but don't appear to be accessible now. |  |  |  |
| Evidence | It's difficult to prove that our current initiatives have the desired impact. As a result, it's difficult to create robust arguments for their continued, or expanded, funding. |  |  |  |
| Data quality checking | (pending) |  | Education levels can potentially be used as a proxy flag point from which to check data for other issues. For example, in an area with low high-school completion rates, we can expect high crime and high rates of long-term health conditions. |  |
| Data quality | Some data is of low quality. It doesn’t tell us much that’s of use. |  |  | ABS data in particular. |
| Data gaps | Lack of robust data to prove outcome efficacy of existing programmes |  |  |  |
| Data comparison gaps | Lack of ability to compare outcome-based metrics across different remote communities |  |  |  |
| Data – Census | Census data for many indigenous communities appears to be incorrect. There appear to be issues with standard methods of census data collection when it comes to indigenous communities. | Accurate census data, and better understanding by government of the situation in communities. |  | Current census data for communities quickly shows inconsistencies e.g.: Rates shown in census results for long-term health condition rates, population age distribution, household occupancy rates, even basic population levels - all these numbers are not consistent with people's lived experience. |
| Data | People can’t find data that exists. Some of its appears to be almost hidden. |  |  |  |
| Data | The data is there, but it’s in silos – disconnected and held by groups that don’t necessarily communicate. |  |  |  |

## Potential initial metrics

This table introduces some potential metrics for consideration.

It’s expected that the process of consultation with academic experts and indigenous communities, most of these measures will be replaced.

| Category | Sub-Category | Item | Description | Why this is important | Measure(s) of success | Potential sources |
| --- | --- | --- | --- | --- | --- | --- |
| Children |  | Age of mother at birth of first child | The median age of new mothers in the community. | a) The age of a child’s mother can significantly impact lifetime outcomes of the child. b) The age at which a woman has her first child is a powerful proxy measure of girls’ education, gender equality, the control young women have of their own lives, and, arguably, levels of locus of control in the community. | Increasing median age over time. | (TBD) |
| Children |  | Early childhood development | Measures of how well children are developing in their early stages. Focused on early childhood – age three and below. | Extensive research has shown that what happens in a child’s first few years lays critical foundations for how they interact with the world throughout their lives. Children who, in their earliest years, are physically healthy, verbal and emotionally secure are less likely to have major issues later in life. |  | (TBD) |
| Children |  | Early childhood issues | Instances of health issues (physical and mental) in early childhood. Focused on early childhood – age three and below. |  |  | (TBD) |
| Closing the Gap | CtG Target 10 | Adults are not overrepresented in the criminal justice system | Aboriginal and Torres Strait Islander people are not overrepresented in the criminal justice system. |  | By 2031, reduce the rate of Aboriginal and Torres Strait Islander adults held in incarceration by at least 15 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 02 | Children are born healthy and strong | Aboriginal and Torres Strait Islander children are born healthy and strong. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander babies with a healthy birthweight to 91 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 03 | Children are engaged in high quality, culturally appropriate early childhood education in their early years | Aboriginal and Torres Strait Islander children are engaged in high quality, culturally appropriate early childhood education in their early years. |  | By 2025, increase the proportion of Aboriginal and Torres Strait Islander children enrolled in Year Before Fulltime Schooling (YBFS) early childhood education to 95 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 12 | Children are not overrepresented in the child protection system | Aboriginal and Torres Strait Islander children are not overrepresented in the child protection system. |  | By 2031, reduce the rate of over-representation of Aboriginal and Torres Strait Islander children in out-of-home care by 45 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 04 | Children thrive in their early years | Aboriginal and Torres Strait Islander children thrive in their early years. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander children assessed as developmentally on track in all five domains of the Australian Early Development Census (AEDC) to 55 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 16 | Cultures and languages are strong, supported and flourishing | Aboriginal and Torres Strait Islander cultures and languages are strong, supported and flourishing. |  | By 2031, there is a sustained increase in number and strength of Aboriginal and Torres Strait Islander languages being spoken. | Closing the Gap web site |
| Closing the Gap | CtG Target 01 | Everyone enjoys long and healthy lives | Aboriginal and Torres Strait Islander people enjoy long and healthy lives. |  | Close the Gap in life expectancy within a generation, by 2031. | Closing the Gap web site |
| Closing the Gap | CtG Target 13 | Families and households are safe | Aboriginal and Torres Strait Islander families and households are safe. |  | By 2031, the rate of all forms of family violence and abuse against Aboriginal and Torres Strait Islander women and children is reduced at least by 50%, as progress towards zero. | Closing the Gap web site |
| Closing the Gap | CtG Target 09 | People can secure appropriate, affordable housing that is aligned with their priorities and need | Aboriginal and Torres Strait Islander people secure appropriate, affordable housing that is aligned with their priorities and need. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander people living in appropriately sized (not overcrowded) housing to 88 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 14 | People enjoy high levels of social and emotional wellbeing | Aboriginal and Torres Strait Islander people enjoy high levels of social and emotional wellbeing. |  | Significant and sustained reduction in suicide of Aboriginal and Torres Strait Islander people towards zero. | Closing the Gap web site |
| Closing the Gap | CtG Target 17 | People have access to information and services enabling participation in informed decision-making regarding their own lives | Aboriginal and Torres Strait Islander people have access to information and services enabling participation in informed decision-making regarding their own lives. |  | Target 17: By 2026, Aboriginal and Torres Strait Islander people have equal levels of digital inclusion | Closing the Gap web site |
| Closing the Gap | CtG Target 15 | People maintain a distinctive cultural, spiritual, physical and economic relationship with their land and waters | Aboriginal and Torres Strait Islander people maintain a distinctive cultural, spiritual, physical and economic relationship with their land and waters. |  | 1. By 2030, a 15 per cent increase in Australia’s landmass subject to Aboriginal and Torres Strait Islander people’s legal rights or interests. 2. By 2030, a 15 per cent increase in areas covered by Aboriginal and Torres Strait Islander people’s legal rights or interests in the sea. | Closing the Gap web site |
| Closing the Gap | CtG Target 08 | Strong economic participation and development of people and their communities | Strong economic participation and development of Aboriginal and Torres Strait Islander people and communities. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander people aged 25-64 who are employed to 62 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 05 | Students achieve their full learning potential | Aboriginal and Torres Strait Islander students achieve their full learning potential. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander people (age 20-24) attaining year 12 or equivalent qualification to 96 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 06 | Students reach their full potential through further education pathways | Aboriginal and Torres Strait Islander students reach their full potential through further education pathways. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander people aged 25-34 years who have completed a tertiary qualification (Certificate III and above) to 70 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 10 | Young people are not overrepresented in the criminal justice system | Aboriginal and Torres Strait Islander young people are not overrepresented in the criminal justice system. |  | By 2031, reduce the rate of Aboriginal and Torres Strait Islander young people (10-17 years) in detention by 30 per cent. | Closing the Gap web site |
| Closing the Gap | CtG Target 07 | Youth are engaged in employment or education | Aboriginal and Torres Strait Islander youth are engaged in employment or education. |  | By 2031, increase the proportion of Aboriginal and Torres Strait Islander youth (15-24 years) who are in employment, education or training to 67 per cent. | Closing the Gap web site |
| CYP Proxy measures | Savings rates | Amounts saved in CYP-managed saving products | How much people have saved in the products / services that CYP manages and/or monitors. Total and median savings, among O-Hub clients and a representation of median across the total community. |  |  | CYP data (2022) |
| CYP Proxy measures | Digital uptake | Use of digital products | Proportion of the community using CYP digital products |  |  | CYP data (2022) |
| CYP Proxy measures | Service use | Use of O-Hub services | Proportion of the community using O-Hub services |  |  | CYP data (2022) |
| Education |  | Ability to manage own finances | The proportion of community members who demonstrate that they are able to save for, and achieve, a financial goal, and are able to plan for future financial demands (both expected and unexpected) e.g.: bills, funeral costs, rates, repair costs etc). |  |  | CYP data (2022) |
| Education |  | Ability to self-manage official correspondence | The ability of community members to independently receive, understand, and productively deal with information and/or instructions from official sources (government, councils, financial institutions etc). Self-reported, based on participant survey results. |  |  | CYP data (2022) |
| Education |  | Education – Highest level of education reached | The level of schooling completed (i.e.: which year of school). Both median and average values should ideally be monitored. | Education is a critical enabler for people to control their own lives. Education is also a strong predictor of lifetime outcomes, such as income levels and ability to manage challenges in one’s life. |  | CYP data (2022) |
| Employment |  | Employment levels | The percentage of people in the community of working age who are currently in active paid employment |  |  | (TBD) |
| Finance |  | Home ownership rates | The percentage of families in the community that own the home they live in |  |  | (TBD) |
| Finance |  | Median net asset base | How much money people have saved up, plus any valuable assets they own, minus debts. |  |  | (TBD) |
| Health |  | Health - diabetes | The proportion of the population with mental health issues (both diagnosed and estimated) |  |  | (TBD) |
| Health |  | Health – foetal alcohol syndrome | The proportion of the children born that demonstrate signs of foetal alcohol syndrome |  |  | (TBD) |
| Health |  | Health – hearing issues | The proportion of the population with hearing issues (both diagnosed and estimated) |  |  | (TBD) |
| Health |  | Health – mental health issues | The proportion of the population with mental health issues (both diagnosed and estimated) |  |  | (TBD) |
| Health |  | Health professionals per population | How many qualified health professionals (of all important fields) there are per unit of population (e.g.: per 100,000 people. Include GPs, mental health professionals (psychologists, counsellors, psychiatrists etc). |  |  |  |
| Health | Mortality | Suicides | Rates of death by suicide in monitored communities. May include a sub-measure of suicide attempts. | Initiatives to reduce high suicide rates are defined and known. There are many things that can be done. What is needed is explicit linkage between funded suicide prevention initiatives and actual suicide / attempted suicide rates. |  |  |
| Health | Mortality | Early deaths |  |  |  |  |
| Health | Drug use | Rates of problematic drug use in the community | Rates of drug use in the community that is at levels that create adverse impacts on individuals, or the community as a whole. Includes both legal drugs (e.g.: alcohol) and illicit drugs, using known and estimated rates. |  |  | (TBD) |
| Inequality |  | Median income relative to median cost of living |  | In places where the cost of living is higher (such as cities with high rent, or remote communities with high food & product costs), the real "lived" relative income will be lower. |  |  |
| Judiciary | Crime rates | Instances of criminal activity | Instances of criminal activity each year in a community. Measured annually, covering both formally reported crimes, and estimations of true rates. |  |  | (TBD) |
| Judiciary | Criminal convictions | Proportion of the population convicted of criminal offences | The proportion of the population that has been found guilty of a crime. Measured both annually, and across individual’s lifetimes. |  | Lowering conviction rates over time. Lowering proportion of the population with a criminal history. | (TBD) |
| Safety |  | Domestic violence levels | Rate of incidence of acts of domestic violence – both official figures, and estimations of true rates. |  |  | (TBD) |

## Initiative component list

The list below provides an initial indication of the stages that might be included in an initiative (project) to create and implement Community Uplift metrics.

| Ref | Initiative Component Heading | Description | Stakeholders | Contributors (types) | Comments |
| --- | --- | --- | --- | --- | --- |
|  | Define the initiative (part 1/2) | First iteration to define the initiative – by the initial team. |  |  |  |
|  | Build multi-organisational appetite | The activity of getting a sufficient number of organisations (indigenous and other) on board to actively participate in this initiative, help to define it, and help to make it progress). |  |  |  |
|  | Expand the team | Having built appetite and commitment across organisations, bring in additional expertise to help set the path and make it happen |  |  |  |
|  | Enhance the core concepts | As input to the business case, work with all stakeholders so far identified to define and articulate the core concepts of the initiative, including the long-term change we aim to create, the components of that, the metrics to guide that, and what will be needed to get there. |  |  |  |
|  | Develop the business case | Co-design and create a robust business case for the initiative to be presented, to potential funding organisations |  |  |  |
|  | Obtain funding | Engage with potential sponsors and funders to obtain the funds to design, develop and operationalise the Community Uplift Metrics initiative. |  |  |  |
|  | Define community capability uplift | Define the improvement needed. Determine, and gain agreement on, what is important to help remote communities build their own self-sustaining capability |  | - Indigenous community leaders - Social development researchers | Note: The “Closing the Gap” measures would be one of the important inputs to this activity. |
|  | Determining what should to be measured | Work with impacted indigenous communities, experts in the field (academics etc) and other key stakeholders to build an initial concept of measurement and community improvement |  | - Indigenous community leaders - Social development researchers | Note: The “Closing the Gap” measures would be one of the important inputs to this activity. |
|  | Define the metrics | Using the descriptions of what should be measured, and what “capability uplift” means, identify the individual data items that will measure current state, and improvement over time. Clear metrics need to be identified for focus areas that build an objective understanding of, and proof of, the impact being created in the targeted communities. These metrics should focus where community capability uplift is most valuable – both for those on the ground, and in areas that social policy researchers focus for gauging inter-generational improvements in the health of communities. |  | - Indigenous community leaders - Social development researchers - Epidemiologists |  |
|  | Define the initiative (part 2/2) | 2nd iteration to define the scope of the initiative (project), including how to build active support, and how to turn these metrics in to drivers for community capability development. |  |  |  |
|  | Build the data platform | Design and build the technology for collecting, storing, managing, analysing and sharing the metrics data. Must include extensive user-centred design, focusing not only on those who will directly use the technology, but also on the social impact the technology aims to create, and how that context should impact technology architecture. | - All contributors to metrics definition Indigenous communities throughout the country - Non-indigenous remote communities throughout the country |  |  |
|  | Build national data collection capability | Develop the tools, technology, skills, agreements and services to enable collection of data from all impacted communities and groups. |  |  |  |
|  | Collect the data | Having determined important areas to measure, investigate and implement the collection, storage and analysis of the data across as wide a set of data sources as is possible. |  |  |  |
|  | Build national data use capability | Guide the development of capability around the country to make good use of the data that will be collected, collated and linked. |  |  |  |
|  | Influence national capability development goal conversations | Conduct separate communications initiatives to influence national conversations about what should ideally be measured to best create community capability uplift |  |  |  |
|  | Develop data utilisation capability | Conduct separate initiatives to help communities, researchers and government agencies to use the data for its intended purpose. |  |  |  |
|  | Establish iterative improvement frameworks | Design and implement a framework, schedule and resource commitment for ongoing improvement of the Community Uplift Metrics initiative, goals, data, technology, communications and education. |  |  |  |
|  | Move to operationalisation | Decommission the creation initiative and switch to sustained operation of the Community Uplift Metrics ecosystem. |  |  |  |
|  | Continuously improve | Using open, cooperative, cross-disciplinary co-design approaches, implement continuous improvement of the model and data approaches to progressively enhance not only the data itself, but cross-community understanding of the data and its value. |  |  |  |

## References

- Berlin, Isiah (1969) Two Concepts of Liberty in “Four Essays On Liberty”, Oxford, England: Oxford University Press, 1969, p. 118-172. ISBN 0195012429.

      - Full paper available at: https://cactus.utahtech.edu/green/B_Readings/I_Berlin%20Two%20Concpets%20of%20Liberty.pdf.

      - A description of the book’s four essays is available at www.ebsco.com/research-starters/literature-and-writing/four-essays-liberty-isaiah-berlin.

      - A description of Positive and Negative Liberty is available at https://plato.stanford.edu/entries/liberty-positive-negative.

- Dodson, Mick; Smith, Diane (2003) Governance for sustainable development: Strategic issues and principles for Indigenous Australian communities, Centre for Aboriginal Economic Policy Research, Australian National University. ISSN 1036-1774. ISBN 0 7315 5625 9. https://openresearch-repository.anu.edu.au/bitstream/1885/41862/3/Dodson_GovernanceSustainable2003.pdf.

- Doering, Nina; Dudeck, Stephan; Elverum, Shelly; Fisher, Charleen; Henriksen, Jan; Herrmann, Thora; Kramvig, Britt; Laptander, Roza; Milton, Justin; Omma, Elle (2022) Improving the Relationships Between Indigenous Rights Holders and Researchers in the Arctic: An invitation for Change in Funding and Collaboration, Environmental Research Letters, Volume 17, Number 6. www.doi.org/10.1088/1748-9326/ac72b5.

- Jordan, Kirrily; Markham, Francis; Altman, Jon (2020) Linking Indigenous Communities with Regional Development: Australia Overview, Commissioned Report No. 5, Centre for Aboriginal Economic Policy Research, Australian National University. www.doi.org/10.25911/5f7edceea4190.

- Markham, Francis, Smith, Diane & Morphy, F. (2020). Indigenous Australians and the COVID-19 crisis: perspectives on public policy, Topical Issue no. 1/2020, Centre for Aboriginal Economic Policy Research, Australian National University, Canberra. www.doi.org/10.25911/5e8702ec1fba2.

- Sen, Amartya Kumar (1999) Development as Freedom. ISBN 0-3 7 5-40619-0.

      - Full book available at: www.c3l.uni-oldenburg.de/cde/OMDE625/Sen/Sen-intro.pdf.

- Sharma-Wallace, Lisa; Velarde, Sandra; Edwards, Peter; Warmenhoven, Tui; Pohatu, Pia (2020) Exploring Adaptive Governance for Indigenous Peoples: Lessons from Aotearoa New Zealand’s Erosion Control Funding Programme, Society & Natural Resources, 33:1, 1-24, www.doi.org/10.1080/08941920.2018.1557308.